## List of deliverables
List of project's deliverables |  |  | (SG2)
Deliverable code | Deliverable name | Deliverable descr. | Deliverble type | Priority | Due date | Dependencies
D1 | Final publication | Publication of the remaining part of the corpus | Data | 3 | month 6 | D3,D4,D5
D2 | Location script | Fix location gap in the RDF | Code | 4 | month 6 | D5
D3 | KWICKWOCKWAC | KWICKWOCKWAC Fix | Code | 1 | month 3
D4 | Training | Researchers training | Training | 1 | month 4 | D3 (not strict)
D5 | ETL | ETL procedure (python code) fix | Code | 2 | month 4
D6 | Documentation | Improve documentation | Documentation | 5 | month 7
D7 | New webpage | Complete bio webpage | Web | 6 | month 7

## List of activities
List of project's activities (WBS) |  |  |  | (SG3)
Task code | Task title | Activity type | Activity descr. | Owner | Start date | Due date | Duration (est.) | Effort (est.) | Priority | Sequence | Dependencies | WBS No. | Deliverable affected
T1 | KWICKWOCKWAC assessment | Analisys | Collect Release Notes and set the state of the art of the application | Erica | [8 empty] | D4
T2 | KWICKWOCKWAC connectivity | Analisys | Verify connectivity with WikiData and Treccani | Erica | [8 empty] | D4
T3 | KWICKWOCKWAC Fix | Development | Fix of bugs | Prof. Vitali | [8 empty] | D4
T4 | KWICKWOCKWAC deploy | Deploy | KWICKWOCKWAC deployed to the AME environment | Prof. Vitali | [8 empty] | D4
T5 | Researchers training | Training | Trining on new KWICKWOCKWAC features | Erica and Luisa | 2023-11-20 | 2023-12-07 | [6 empty] | D5
T6 | ETL validation | Testing | ETL functionalities assessment | Erica | 2023-10-15 | 2023-11-24 | [6 empty] | D6
T7 | ETL fix | Development | ETL fixing and improvments | Erica and Luisa | 2023-10-16 | 2023-11-24 | [6 empty] | D6
T8 | ETL test and deploy | Testing | ETL validation | Erica and Luisa | 2023-11-24 | 2024-01-01 | [6 empty] | D6
T9 | Corpus annotation | Data curation | Document being annotated by researchers | Researchers team | 2023-11-27 | 2024-01-20 | [6 empty] | D1
T10 | ETL run | Development | Runnign the ETL to prepare the dataset for publication | Erica | 2023-11-27 | 2024-02-25 | [6 empty] | D1
T11 | Dataset quality assessment | Testing | Dataset quality assessment | Erica and Luisa | 2023-12-01 | 2024-03-15 | [6 empty] | D1
T12 | Dataset publication | Deploy | Dataset publication | Erica | 2024-01-15 | 2024-03-28 | [6 empty] | D1
T13 | Requirements refinement | Analisys | Requirements refinement for D2 and D3 | Erica | [8 empty] | D2, D3
T14 | Documentation assessment and refinement | Analisys | Documentation assessment and refinement | Erica and Luisa | [8 empty] | D7
T15 | Document delivery | Deploy | Document delivery | Erica and Luisa | [8 empty] | D7
T16 | Bio webpage | Web Dev | Complete bio webpage | Erica and Luisa
| TOTALS | [5 empty] | 0 | 0

## List of resources
List of project's resources |  |  | (SG3)
Resource type | Resource name | Resource code | Max effort
Dev and Analyst | Erica |  | 6 p/m
Researcher | Valentina Casini |  | 1,5 p/m
Researcher | Michele Cento |  | 1,5 p/m
Editor | Luisa |  | 6 p/m
Coordinator | Pasquale |  | 6 p/m
Internship | Gionata |  | 0,25 p/m
Manager | Maria Laura |  | 6 p/m

## Gantt Chart
Project plan (Gantt chart) | [31 empty] | https://goo.gl/PXLbMe
PROJECT
PROJECT MANAGER
[6 empty] | OCTOBER 23 | [19 empty] | NOVEMBER 23 | [19 empty] | DECEMBER 23 | [19 empty] | January 2024 | [19 empty] | February 2024 | [14 empty] | March 2024
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Analysis
1.1 | Researchers training | Erica and Luisa | 2023-11-20 | 2023-12-07 | 17 | bar: WEEK 3 M to WEEK 1 R
1.1.1 | ETL validation | Erica | 2023-10-15 | 2023-11-24 | 39 | bar: WEEK 2 F to WEEK 3 F
1.2 | ETL fix | Erica and Luisa | 2023-10-15 | 2023-11-24 | 39 | bar: WEEK 2 F to WEEK 3 F
1.3 | ETL test and deploy | Erica and Luisa | 2023-11-24 | 2023-12-20 | 26 | bar: WEEK 2 F; WEEK 4 M to WEEK 2 F
1.4 | Corpus annotation | Researchers team | 2023-11-20 | 2024-01-15 | 55 | bar: WEEK 2 F; WEEK 3 T to WEEK 11 F
2 | Design and Development | bar: WEEK 1 M to WEEK 12 F
2.1 | ETL run | Erica | 2023-11-27 | 2024-02-20 | 83 | bar: WEEK 2 F; WEEK 4 F to WEEK 14 M; WEEK 1 M to WEEK 4 T
2.2 |  |  |  |  | 0 | bar: WEEK 2 F
2.3 |  |  |  |  | 0 | bar: WEEK 2 F
2.4 |  |  |  |  | 0 | bar: WEEK 2 F
3 | Testing and roll-out
3.1 | Dataset quality assessment | Erica and Luisa | 2023-12-01 | 2024-03-15 | 104 | bar: WEEK 2 F; WEEK 4 F to WEEK 14 R; WEEK 1 M to WEEK 4 T
3.2 | Dataset publication | Erica | 2024-02-15 | 2024-03-25 | 40 | bar: WEEK 2 F; WEEK 12 F to WEEK 14 R; WEEK 3 M to WEEK 4 F
3.3 |  |  |  |  | 0 | bar: WEEK 2 F
3.4 |  |  |  |  | 0 | bar: WEEK 2 F
EST. TOTAL EFFORT = ? |  |  |  |  | 430